## Sheet1
SEVERITY
| Risk | Result | Response | Likelihood | Impact | Risk Level | Date of RS | Revisited | Comments |  |  | Minimal | Minor | Moderate | Major | Severe
| Hardware failure or Software) | Hardware fails or software is corrupt | Have other hardware available, back up for data and other software | Likely | Servere | 15 | 2021-04-27 | 04/05/2021 & 20/5/2021 | Laptop software installed incorrectly | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
| Software failure | App refused to connect to GCP VM so I was unable to do test in venv | Try creating other VM and copies of App | Likely | Servere | 15 | 2021-04-27 | 21/05/21 & 23/5/21 | Unable to do Testing integration in venv |  | Expected | 4 | 8 | 12 | 16 | 20
| Accidental human interference | Accidentally deleting files | Configure permissions properly and back up regularly | Likely | Major | 12 | 2021-04-27 | 2021-05-19 | Creating a DB in Workbench |  | Likely | 3 | 6 | 9 | 12 | 15
| DDOS Attack | Causes a denial of service for users, i.e. unabvle to log in the app | Configure the firewall properly and have good DDOS mitigation | Possible | Servere | 10 | 2021-04-27 | 2021-05-23 | Recreated new venv and new firewalls |  | Possible | 2 | 4 | 6 | 8 | 10
| Users forget passwords | User won't be able to login | Recover your password options | Guaranteed | Minimal | 5 | 2021-04-27 | 30/4/2021 & 20/05/2021 | Too many passwords |  | Unlikely | 1 | 2 | 3 | 4 | 5
1 | User passwords can be guessed or cracked | Hacker will have access to user's information | Password policy in place(must have letters, numbers and symbols…) | Possible | Minor | 4 | 2021-04-27 | 2021-05-17 | No way I can cracke it
2 | Data leakage/theft | Access to database | Access to database managed by multifactor authentication | Possible | Servere | 10 | 2021-04-27
7 | Data Encryption | Data will be exposed | Make sure app connects to web services using secure connection protocols such as HTTPS. | Possible | Moderate | 6 | 2021-04-27
8 | Apps new features released | Denied access to Repo from Git Bash | Re-installed or update the app | Likely | Moderate | 9 | 2021-04-27 | 2021-05-22 | Unable to push to repo due to Credential Manager in GitHub

## Sheet2
Description | Assessment | Risk | Impact | Responsibility | Current Mitigation | Proposed Mitigation | Response | Tolerance
Database is attacked (e.g. SQL injection) and data is breached | Can lead to attackers being able to read any information stored in the database, including user emails and passwords. The data stored in this database is not sensitive outside of the passwords – if the user uses this password on multiple accounts online it can leave them open to being hacked. | Low | Medium | Harry Volker | Passwords are hashed before being stored on the database, so users' passwords are never retained. This means the only risk would be if the user is using a common password and the attacker can figure out the hash. | Suggest that the user does not use a commonly used password for their account when signing up for the service. Implement back-end code to prevent SQL injections. | Bring the database offline and inform users via email that this information has been breached. Recommend that they change their passwords for other services that share breached password. | Tolerate
Database is deleted by attackers | Attackers can use SQL injections to drop tables and entire databases. Ultimately, while not ideal, the information stored in this app's database is low-importance, so the impact of this kind of attack is low. | Low | Low | Harry Volker | None | Regularly backup database on another machine to recall data in the case of data loss. | Rebuild the infrastructure of the database from the VM terminal, as it is all created using SQLAlchemy and would be quick to implement. If user emails are lost, post information on the home page to inform users that the information has unfortunately been lost and they will have to create a new account | Tolerate
HTTP traffic is monitored by an attacker | Connection between machines on the cloud network is currently insecure, meaning that information being sent via HTTP across the network can be easily monitored by individuals with malintent. Biggest risk is between the user and the web server as password information is sent unhashed and unencrypted. | High | High | Harry Volker | None | Set up HTTPS connection across the network to encrypt information going to and from the system | If this occurs, it is unfortunately unlikely that we will be aware. If we are made aware, inform users via email that their information has been compromised and to change their passwords on other accounts should they use them elsewhere. | Treat
SQL database goes dark | If the SQL database service (provided by GCP) shuts down, the website will be rendered non-functional. | Low | Low | Google Cloud Platform | None | Set up a backup SQL database in the case of an outage | Bring website down. Attempt to spin the SQL database back up. Contact GCP for reasons why this occurred and possible mitigation in the future. | Tolerate
Web server goes dark | If the VM running the Flask web server (provided by GCP) shuts down, the website will be rendered non-functional. | Low | Low | Google Cloud Platform | None | Set up a backup VM to spin up in the case of the first shutting down. | Attempt to spin the server up again. If this doesn't work, spin up a new VM and pull the installation files down from Git to run the server. Contact GCP for reasons why this occurred and possible mitigation in the future. | Tolerate